# Invitation to Tender:

| Tender Name: Construction of Toilets/Latrines (Sanitary Facilities) | Tender No: NIG/BIU/TEN11 |
| --- | --- |
| Locations: Biu and Shani LGAs – Borno State | Correspondence Language(s): English |
| Brief Summary Description of Project: Mercy Corps, an International Non-Governmental Humanitarian Organization is pleased to invite Service providers to submit bids for the upgrade & rehabilitation of water schemes in Biu, Kwaya Kusar & Shani LGAs, Borno State, Northeast – Nigeria under Small Town Wash Project. The Small-Town Water, Sanitation, and Hygiene (STWASH) activity is a five-year, initiative funded by the United States Agency for International Development (USAID), covering the states of Adamawa, Yobe, and Borno in Northeast Nigeria. The Activity is to support the sustainable improvements in access to basic water and sanitation that are necessary to facilitate ongoing recovery, peacebuilding, and economic development across the region. The goal of the program is to facilitate the economic recovery of some crisis-affected communities and bolster the capacity of the state governments in providing essential WASH services and creating and sustaining enabling environments for Small Towns Water Supply and Sanitation Agencies (STWSSAs) and Water Consumers Associations (WCAs) to operate effectively. The program has two broad components: expanded access to water and for sanitation facilities and strengthening capacity for small town water governance. Mercy Corps chooses to hold competitive process for the selection of companies/contractors who will implement our requirements. We believe that competitive bids are the only way to fairly select the best company for the job while ensuring good prices and preventing collaboration and corruption. |  |

| Tender Package Available from: 30th September 2021 @ 8:00am | Tender Package Pickup Location: Tenders can be accessed on https://www.mcnigeria.com/tenders/ |
| --- | --- |
| Deadline for Offer Submission: 12th October 2021 @ 5:30pm | Submit Offers to: - For Physical submissions: Full bidding document with attachments in sealed envelope to Mercy Corps Office in Biu, Nigeria located at; Behind BOSADP Office, Tse-Tse, Adjacent PS House, Biu, Borno State, Nigeria - For electronic submissions: Email a full bid document with attachments to tenders@mercycorps.org Note: Envelopes or emails should be marked as per below Tender No. NIG/BIU/TEN11 Tender Name: Construction of Toilets in Biu & Shani LGAs, Borno State, Nigeria. |

Mercy Corps reserves the right to accept or reject any late offers

| Questions and Answers (Q&A) |  |
| --- | --- |
| If any, Submit Questions in writing to: qa-ng-tenders@mercycorps.org |  |
| Last Day for Questions: 7th October 2021; | Questions will be answered by: 8th October 2021; |
| Questions will be answered through: https://www.mcnigeria.com/tenders |  |

| Documentation Checklist |  |
| --- | --- |
| These documents are contained within this tender package: | - Invitation to Tender - General Conditions for Tender - Criteria and Submittals - Price Offer Sheet - Supplier Information Form - Technical Specifications/BoQ - Sample Contract |

# General Conditions for Tender

Mercy Corps invites offers for the goods described and summarized in these documents, and in accordance with procedures, conditions and contract terms presented herein. Mercy Corps reserves the right to vary the quantity of work/materials specified in the Tender Package without any changes in unit price or other terms and conditions and to accept or reject any, all, or part of submitted offers. The supplier will be responsible to deliver the entire order to Mercy Corps Designated sites within Borno State.

2.1	Mercy Corps’ Anti-Bribery and Anti-Corruption Statement

Mercy Corps strictly prohibits:

- Any form of bribe or kickback in relation to its activities

This prohibition includes any request from any Mercy Corps employee, consultant or agent for anything of value from any company or individual in exchange for the employee, consultant or agents taking or not taking any action related to the award of a contract or the contract once awarded.  It also applies to any offer from any company or individual to provide anything of value to any Mercy Corps employee, consultant or agent in exchange for that person taking or not taking any action related to the award of the contract or the contract.

- Conflicts of interests in the awarding or management of contracts

If a company is owned by, whether directly or indirectly, in whole or in part, any Mercy Corps employee or any person who is related to a Mercy Corps employee, the company must ensure that it and the employee disclose the relationship as part of or prior to submitting the offer.

- The sharing or obtaining of confidential information

Mercy Corps prohibits its employees from sharing, and any offerors from obtaining, confidential information related to this solicitation, including information regarding Mercy Corps’ price estimates, competing offerors or competing offers, etc.  Any information provided to one offeror must be provided to all other offerors.

- Collusion between/among offerors

Mercy Corps requires fair and open competition for this solicitation.  No two (or more) companies submitting bids can be owned or controlled by the same individual(s). Companies submitting offers cannot share prices or other offer information or take any other action intended to pre-determine which company will win the solicitation and what price will be paid.

Violations of these prohibitions, along with all evidence of such violations, should be reported to:

integrityhotline@mercycorps.org

Mercy Corps will investigate allegations fully and will take appropriate action.  Any company, or individual that participates in any of the above prohibited conduct, will have its actions reported to the appropriate authorities, will be investigated fully, will have its offer rejected and/or contract terminated, and will not be eligible for future contracts with Mercy Corps. Employees participating in such conduct will have his/her employment terminated.

Violations will also be reported to Mercy Corps’ donors, who may also choose to investigate and debar or suspend companies and their owners from receiving any contract that is funded in part by the donor, whether the contract is with Mercy Corps or any other entity.

2.2 	Tender Basis:

- All offers shall be made in accordance with these instructions, and all documents requested should be furnished, including any required (but not limited to) supplier-specific information, technical specifications, drawings, bill of quantities, and/or delivery schedule. If any requested document is not furnished, a reason should be given for its omission in an exception sheet.

- No respondent should add, omit or change any item, term or condition herein.

- If suppliers have any additional requests and conditions, these shall be stipulated in an exception sheet.

- Each offeror may make one response only.

- Each offer shall be valid for the period of [120 days] from its date of submission.

- All offers should indicate whether they include taxes, compulsory payments, levies and/or duties, including VAT, if applicable.

- Suppliers should ensure that financial offers are devoid of calculation errors. If errors are identified during the evaluation process, the unit price will prevail. If there is ambiguity on the unit price, the Selection Committee may decide to disqualify the offer.

- Any requests for clarifications regarding the project that are not addressed in written documents must be presented to Mercy Corps in writing. The answer to any question raised in writing by any offeror will be issued to that offeror. In some cases Mercy Corps may choose to issue clarifications to all offerors. It is a condition of this tender that no clarification shall be deemed to supersede, contradict, add to or detract from the conditions hereof, unless made in writing as an Addendum to Tender and signed by Mercy Corps or its designated representative.

- This Tender does not obligate Mercy Corps to execute a contract nor does it commit Mercy Corps to pay any costs incurred in the preparation and submission of bids. Furthermore, Mercy Corps reserves the right to reject any and all offers, if such action is considered to be in the best interest of Mercy Corps.

- The supplier will be responsible to deliver the entire order to

Mercy Corps designated sites, Borno State - Nigeria.

2.3 	Supplier Eligibility

Suppliers may not apply, and will be rejected as ineligible, if they:

- Are not registered companies

- Are bankrupt or in the process of going bankrupt

- Have been convicted of illegal/corrupt activities, and/or unprofessional conduct

- Have been guilty of grave professional misconduct

- Have not fulfilled obligations related to payment of social security and taxes

- Are guilty of serious misinterpretation in supplying information

- Are in violation of the policies outlined in Mercy Corps Anti Bribery or Anti-Corruption Statement

- Supplier (or supplier’s principals) are on any list of sanctioned parties issued by; or are presently excluded or disqualified from participation in this transaction by: The United States Government or United Nations by the United States Government, the United Kingdom, the European Union, the United Nations, other national governments, or public international organizations.

Additional eligibility criteria, if applicable, are stated in section 3.2 of this tender package.

2.4   	Response Documents

Offerors must submit an offer in their own format and ensure it contains all the required documents and information specified in this tender. Where an itemized Price Offer Sheet is included in the tender package, the offeror must complete and submit it with the rest of their offer.

2.5	Acceptance of Successful Response

Documentation submitted by offerors will be verified by Mercy Corps. The winning offeror will be required to sign a contract for the stated, agreed upon amount.

2.6	Certification Regarding Terrorism

It is Mercy Corps’ policy to comply with humanitarian principles and the laws and regulations of the United States, the European Union, the United Nations, the United Kingdom, host nations, and other applicable donors concerning transactions with or support to individuals or entities that have engaged in fraud, waste, abuse, human trafficking, corruption, or terrorist activity. These laws and regulations prohibit Mercy Corps from transacting with or providing support to any individuals or entities that are the subject of government sanctions, donor rules, or laws prohibiting transactions or support to such parties.

# Criteria & Submittals

3.1 Contract Terms Mercy Corps intends to issue a contract to one or several company(ies) or organization(s). The successful offeror(s) shall be required to adhere to the statement of work and terms and conditions of the resulting contract. The anticipated contract is incorporated in Section 6 herein. By submitting an offer, offerors certify that they understand and agree to all of the terms and clauses contained in Section 6.

3.2 Specific Eligibility Criteria In keeping with Mercy Corps’ guiding principle for procurement, Mercy Corps Nigeria Uses only responsible suppliers who possess the ability to perform successfully under the terms and conditions of a proposed procurement. In addition to the ability to perform, Mercy Corps also consider minimum standards of responsibility to determine which suppliers Mercy Corps will do business with. These standards include. - Being eligible business under applicable laws and regulations of the Federal Republic of Nigeria - Being in good standing with any taxation or legal authority in Nigeria - Having a satisfactory record of performance and business and ethics based on information available to Mercy Corps.

3.3 Tender Submittals Documents and required information listed in tender submittals are necessary in order to support the eligibility criteria and to conduct technical evaluations of received offers (and due diligence). While absence of these documents and/or information does not denote mandatory disqualification of suppliers, the lack of these items has the potential to impact the technical evaluation of an offer severely and negatively. Documents supporting the Eligibility Criteria: - Legal Business Registration (Certificate of business registration with Corporate Affairs Commission for companies or businesses operating in Nigeria) - Latest Tax Registration Certificate (From FIRS or Board of Internal Revenue) - A copy of relevant certificate of membership of a professional body (COREN, NMGS etc.) (Please attach evidence to bid document) Documents to conduct the Technical Evaluation and additional Due Diligence: - Company Profile, 2-page max. - Items Technical Specifications (refer to section 5 for the list of specifications). - Document confirming supplier agrees to delivery Time/Project Schedule (maximum delivery or completion time for suppliers to pass 60 calendar days from the date of signing purchase order). - Document confirming Corporate Capabilities. (Required minimum experience is at least 5 years). - Evidence of financial capability/banking statement to execute the contract if successfully selected - Verifiable evidence of experience and relevant qualification of key personal, copies of certificates - Verifiable evidence of relevant projects successfully executed in Nigeria and evidence of knowledge of relevant industry, this is to include letters of award, certificates of completion, references letter, list of projects and addresses of site locations. Price Offer: The Price offer is used to determine which offer represents the best value and serves as a basis of negotiation before award of a contract. As a Fixed-Price contract, the price of the contract to be awarded will be an all-inclusive fixed price basis, either in the form of a total fixed price or a per-unit/deliverable fixed price. No profit, fees, taxes, or additional costs can be added after contract signing. Offerors must show unit prices, quantities, and total price, as displayed in the Offer Sheet in Section 4. All items must be clearly labeled and included in the total offered price. The transportation cost should be included to total price up to.

3.4 Currency Offers should be submitted in: Nigeria Naira (NGN). Payments will be made in: Nigeria Naira (NGN) through wire transfer.

3.5 Tender Evaluation (LPTA Selection Method) Based on the above submittals, a Mercy Corps Tender Committee will conduct a tender evaluation process. Mercy Corps reserves the right to accept or reject any or all bids, and to accept the offer(s) deemed to be in the best interest of Mercy Corps. MC will not be responsible for or pay for any expenses or losses which may be incurred by any Offeror in the preparation of their tender. Evaluations will be conducted as described in the following subsections:

3.5.1 Technical Evaluation Lowest Price, Technically Acceptable (LPTA) Mercy Corps Tender Committee will conduct a technical evaluation which will grade technical criteria on a pass/fail basis. Supplier’s bids must meet the minimum technical standard established here to receive a passing mark. Any offerors who receive a failing mark on any criteria will be automatically disqualified from the tender process. Only offerors who pass all criteria will move on to the next round of evaluation. Pass/fail technical criteria are as follows: Technical Criteria; Pass or fail?. Evidence of previously done similarly project (service completion report, verifiable relevant contracts successfully executed within Borno State or the Northeast in general). Delivery Time/Project Schedule/work plan (maximum delivery or completion time for suppliers to pass 60 calendar days from the date of signing the contract).. The company’s technical team should comprise at a minimum; Civil Engr, Geologist, Water Engineering, or any other relevant field (Attach CV of each of the technical team member – 3-page max for each person). Evidence of financial capacity/banking support to execute the contract if successfully selected- One year bank Statement or two years audited financial report (corporate bank account statement of the company must be recent/ the audited financial report should 2018 upward).. A copy of relevant certificate of membership of a professional body (COREN, COMEG, NMGS etc.). At least 5 years of experience in the planning, designing, and overseeing WASH related construction and maintenance of building structures, and At least 5 years’ experience of implementing and/ or rehabilitation, upgrading and construction of WASH related projects;. Financial Offer (Only realistic and reasonable offer will be considered) – Lowest bid received will be considered as the best offer for this tender..

3.5.2 Financial Evaluation and Price/Cost Analysis All suppliers who passed all technical criteria will move on to the financial evaluation where the lowest price offer(s) will be accepted as the winning offeror(s) assuming the price is deemed fair and reasonable and subject to the additional due diligence in section 3.5.3.

3.5.3 Additional Due Diligence Upon completion of both the technical and financial evaluations Mercy Corps may choose to engage in additional due diligence processes with a particular offeror or offeror(s). The purpose of these processes is to ensure that Mercy Corps engages with reputable, ethical, responsible Suppliers with solid financials and the ability to fulfill the contract. Additional due diligence may take the form of the following processes (though it is not limited to): - Reference Checks - Supplier’s facility visits - Analysis of audited financial statements - Determination of relations and affiliations between offerors - Other appropriate documented method giving Mercy Corps increased confidence in the supplier’s ability to perform.

# Offer Form

Offerors must submit their own independent offer including at least (but not limited to): - All documents requested in the “Eligibility Criteria” section of this Tender Package - All documents requested in the “Tender Submittals” section of this Tender Package - All information listed in the “Documents Comprising the Bid” section below All offers must be duly signed (including position and full name of the signer) and stamped, with the date of completion.

Documents Comprising the Bid

The following information must be included in the offer of any potential offeror:

- Cover Letter explaining interest to be a contracted vendor or supplier. The content of the cover letter shall include the following information:

- A detailed specification of the offered items if vary from the required specifications

- Warranty.

- Delivery time

- Price validity date (for this purpose and as stated on the advertisement, quote given shall remain unchanged for 180 working days)

- A Price Offer detailing the unit price only using the Price Offer Sheet template provided in section 7

- Completed and signed Mercy Corps Supplier Information Form (template provided in section 7)

- Other important documents offeror feels need to be attached to support their bid

The original bid shall be signed by the offeror, or a person or persons duly authorized to bind the offeror to the contract. Financial offer pages of the bid shall be initialed by the person or persons signing the bid and stamped with the company seal.

Any interlineations, erasures, or overwriting shall be valid only if they are initialed by the person or persons signing the bid.

# Scope of Work/Technical Specifications

# TECHNICAL SPECIFICATIONS

## 5.1.1	General (Definitions)

In the Specifications (as hereinafter defined) the following words and expressions shall have the meanings hereby assigned to them:

(a) “Specification” means this Specification together with the technical details given in the Scope of Works, the Bill of Quantities and, subject to the Engineer’s approval, specifications, and technical details.

(b) “Provided” and its derivatives means the complete design, delivery, installation, testing and commissioning of the works, inclusive of such ancillary services as inspection and witnessed testing at the places of manufacture, workshop and site painting, handling on site, site trials and of all such other services as are noted in the Specification or reasonably necessary for the safe, reliable and efficient completion of the Contract

(c) “Employer” means the ---------------------------------------------------------

(d) “Engineer” means whosoever is duly assigned and empowered by the employer to act in that capacity.

The bidder is to visit and examine the site of works and its surroundings at his own expense and responsible for obtaining and assessing all information that may be necessary for preparing the bid and entering into a contract for executing the works for there is no special consideration for increased cost arising from site condition.  The costs of visiting sites shall be at the bidder’s own expense.

## 5.1.2	Scope of Contract

The Contract comprises: Construction of 6/4 compartments Pour flush toilet and ancillary Septic tank as follows in the following locations –

- Construction of 1unit of 4Nos toilets in Gamji Primary School and UBA school fillin Jirgi Biu, Biu LGA

- Construction of 2 units of 2Nos gender equality toilets in Government Science Secondary School Biu, Biu LGA

- Construction of 1 unit of 4Nos toilets in Shani Motor Park, Shani LGA

- Construction of 2 units of 2Nos gender equality toilets in Shani Main Market, Shani LGA

- Construction of 3 units of 2Nos gender equality toilets in Government Secondary School Shani, Shani LGA

- Construction of 2 units of 2Nos gender equality toilets in Bigaru School, Shani LGA

See attached drawing and design (Annex 1)

## 5.1.3	Work Schedule

The Contractor on acceptance of the contracts shall be expected to submit a comprehensive work schedule which should fall within the agreed period of contract execution to Employer or the Engineer (appointed Supervising Consultant) for approval before mobilization of men, materials and equipment to site.

## 5.1.4	Mobilization and Site take over

The Contractor shall mobilize to site within two weeks of signing the contract. This should include taking over site to commence necessary works. The contractor shall take over site in the presence of the Engineer, LGA WASH Department/ Unit and Community representatives. Site take over Form should be duly completed and signed (Appendix I).

## 5.1.5	Project Sign Board

The contractor shall construct and install the Sign Board on the project site as specified (Appendix II).

## 5.1.6	Documentation to be provided

During the course of the Contract the Contractor shall furnish three copies of each of the following contract records to the Engineer.

(a) 	Sub-orders for materials and services.

(b)	Day - day diary sheets recording of work executed on the Site.

(c)	Site log.

(d)	Monthly progress reports of work in hand under the Contract (including photographs of 	stages of construction)

(e) 	Completion report (including photographs and GPS coordinate)

## 5.1.7	Testing and Inspection

The Contractor shall give notice in writing for the time, date and place of all impending tests so that the Engineer or his representative may be present to witness such tests.  The contractor shall furnish test certificates in triplicate for all tests whether witnessed or not.

As and when the Engineer is satisfied that the material and components are in accordance with the Specification and have passed the prescribed tests, he will notify the Contractor in writing to that effect.

If after inspection or tests, the Engineer decides that the material or component concerned is defective or is not in accordance with the contract, he may reject it by giving to the Contractor, within a reasonable time, notice in writing of his decision and the grounds upon which it is based.

## 5.1.8	Tests on Completion

When the facility is completely erected on Site and ready for service, the Works shall be tested by the contractor and subjected to the prescribed tests in the presence of the Engineer to demonstrate that the facility is functioning satisfactorily under the approved system of operation and control and that the whole conforms to the Specifications.

## 5.1.9	Transport and Storage

The Contractor shall be responsible for the transportation, storage and security of all equipment and material delivered to the site and installed until the Issue of the Certificate of Completion.

## 5.1.10	Civil Works

### General

Under the supervision of the Employer/Engineer, latrines are to be sited in collaboration with the authority of the beneficiary institution/community. The Contractor shall be responsible for all excavation to the required depth as specified in the working drawings.

The septic tank and soak-away should be sited at least 30m from any source of safe water supply and should always be down the gradient (i.e at lower level than the water source). The building should be positioned in a way that promotes adequate ventilation. The latrine if to be sited in floodplain areas where there is danger of flooding during raining season, adequate disaster consideration should be made.

Soil and water table conditions should be carefully investigated prior to selecting sites for the latrine.

Disturbance to vegetation and the surrounding area should be minimized as much as possible during pit excavation and latrine construction.

All inspection chambers and septic tank must be provided with a vent pipe.

### 5.1.10.1	Excavation and Filling

For excavation and Backfilling purpose, the contractor shall comply with the following:

- Assess the nature of the work and the materials to be excavated.

- Excavate pit and trenches to the required depth unless otherwise instructed.  Obtain instructions if this is obtained at a lesser depth than shown on the drawings or is not obtained at the depth shown on the drawings, or if the formation contains soft or hard sports or highly variable material.

- Excavation formations are to be inspected and approved before new work is laid on them.  Give 24 hours written notice of when excavations will be ready for inspection.  Place concrete or other fill as soon as possible after inspection.

- Excavation works are to be manually accomplished. Mechanical excavation, results in higher costs and vibration of earth; which are not desirable for this work. Shovels and hand diggers are therefore of choice; using unskilled labour which is readily available in the community.

- Backfilling and compaction should be done in layers, 150mm or as directed by the engineer.

- In submerged or flooded area, the site is to be dewatered before placing of concrete.

- Anti-termite shall be applied on the surfaces of excavation immediately after excavation before any work is commenced.

- All unused excavated materials must be removed from the construction site.

### 5.1.10.2	Concrete Work

Cast in-situ and precast reinforced concrete slabs are to be used in this project. Good quality concrete slabs require clean and well graded aggregates. It is necessary to ensure the quality of the Cement, Sand, stone, water and reinforcements meet the recommended standards. The construction materials to be used are to be inspected and certified to be of recommended quality by the Employer/Engineer.

The upper surface of the concrete after compaction shall be finished with 1.1 cement- sand mixture to leave the surface smooth.

All reinforced concrete slabs shall be 100mm thick unless instructed otherwise.

Designs are in mandatory professional compliance of BS8110; Regulating structural use of concrete.

Design mixes are as regulated in the Building Regulations 1985.

Mechanical mixing is usually obtainable at higher costs. It is therefore not desirable within the scope of this work. The volume of concrete works here are minor. Shovels, head pans, wheelbarrows, are therefore of choice using semi-skilled and skilled manpower; but concrete and mortar mixing must be done as directed by the engineer.

#### 5.1.10.2.1 Concrete Mix

Concrete mix ratios –1:2: 4

For mortar, the mix ratio shall be from 1:6 to 1:4 for block laying and chucking as approved by the engineer, 1:4 for plastering and 1:1 for surfacing.

The recommended concrete mix for reinforced concrete shall be 1:2:4 while the mix for other concrete works should be same unless otherwise is stated.

#### 5.1.10.2.2   Concreting

A.	Preparation of Surfaces

The contractor is to prepare a platform with concrete on which all concrete mixing is to be done. Concrete should not be mixed on sand or grass surface.

At the time of placing, ensure that surfaces on which concrete is to be placed are clean with no debris, oil or free water. Dewatering (for floodplain areas) is of paramount important to achieve good concrete work.

Before arranging the formworks for casting of precast concrete, thin plastic sheet or clean sheet of paper (the cement bags paper could be used) should be spread on a stiff, level and smooth platform. Casting of concrete (reinforced or plain) on the bare floor would not be accepted.

#### B	Formwork for In Situ and precast Concrete

Generally provide formwork to produce finished concrete work to required dimensions and finishes. During Concrete Placing, secure wedges and other adjusting devices against movement and maintain watching to ensure no movement occurs.

C.	Adverse Weather

Do not place concrete during rain or strong dust storm or during inclement weather condition.

#### 5.1.10.2.3	Placing and Compacting Concrete

A high degree of compaction without segregation should be ensured by providing suitable workability and by employing appropriate placing and compacting equipment and procedures. Full compaction is particularly important in the vicinity of construction and of embedded reinforcement (see BS 8110 Part 1 sections 6.2.9 and 6.2.10) and against previously placed, unhardened concrete.

All concrete for slab, after placing in formworks, shall be thoroughly compacted so that its surface is smooth, dense, even and free from cavities.

All placing and compacting should be carried out under suitable supervision and as soon after mixing as is practicable. Delays in placing may be permitted provided that the concrete can still be placed and fully compacted without the addition of further water except as permitted by 4.10 of BS 5328-3:1990.

Only the volume of concrete needed for a particular stage of work shall be mixed and must be controlled by the labour force available; all mixed concrete must be placed within 35 minutes of mixing.

#### 5.1.10.2.4	Curing and Protection

As soon as concrete has set or immediately after striking formwork cover surfaces of concrete as specified.  Curing and protection should start immediately after the compaction of the concrete to protect it from:

(a) Premature drying out, particularly by solar radiation and wind.

(b) Leaching out by rain and flowing water.

(c) Rapid cooling during the first few days after placing.

(d) High internal thermal gradients.

(e) Low temperature or frost.

(f) Vibration and impact which may disrupt the concrete and interfere with its bond to the reinforcement.

Keep surfaces of concrete continuously covered for not less than 7 days using one of the following methods:

- Retaining forms in position

- Impervious sheet materials

- Absorbent materials, kept damp

- Application of curing compound.

When covering with sheet materials ensure edges are secured throughout specified curing period to prevent draughts passing over surfaces or concrete.

Concrete cures in three stages: initial setting after casting, which takes between 45 minutes to eight hours; final setting, for 7 to 14 days; and hardening, which takes up to 28 days. At a minimum, keep the precast slabs in one place while curing for the final setting period and only move them after the fourteenth day. It is recommended that the slabs be left for 28 days before laying on the pit, although it can be done after 14 days.

Water Retaining Structures (Septic tank, inspection chambers)

These structures are to be made with solid blocks or hollow blocks FILLED SOLID with concrete. The plastering should be of thick gauge (greater than 12.5mm) to make them watertight. The septic tank should be primed after construction.

## 5.1.11	Materials

- Cement

Ordinary Portland cement shall be used for the construction. Any cement that does not comply with the specification or has deteriorated because of dampness or any other cause shall not be used in the works. Cements that satisfy the requirements for Portland cement, are commonly available nationwide, hence of choice. In the case of unfavorable or infested ground condition, special types of cement shall be used as directed by the engineer. For finishing purposes, colored cement shall be used as directed by the engineer.

- Aggregates

The coarse aggregates typically produced by mining a suitable rock deposit and breaking the removed rock down to the desired size using crushers shall be used. It is distinct from gravel which is produced by natural processes of weathering and erosion, and typically has a more rounded shape and is clean and free of clay. Crushed stone or granite or any other engineer approved aggregate shall be used for the construction. The size of the coarse aggregates should be 10 to 20mm diameter. Both smooth and sharp sand would be required (depending on the stage where they are to be deployed) and should be free of clay and debris.

- Steel Reinforcement

All steel reinforcement for the casting of all reinforced concrete work shall be hot rolled high yield deformed bars and 12mm diameter in size unless instructed otherwise. In case of any lapping, the lap length should be at least 600mm. The steel shall be kept clean and free from loose rust, oil, grease, earth, paint, or any material which may impair the bond between the concrete and the reinforcement, or which may cause corrosion of the reinforcement or deterioration of the concrete. The Employer/Engineer shall inspect the reinforcement before casting of concrete.

Note: There is no separate provision for pricing of reinforcements rather their prices are factored in when pricing for any reinforced concrete member.

## 5.1.12	Block work

Blocks should be at least 28 days old before they are used for construction.

All blocks to be used for load bearing walls should have average compressive strength of 3.45N/mm2 and the ones for non-load bearing walls should be 2.5N/mm2.

The web of the hollow blocks should be at least 50mm.

225mm x 225mm x 450mm (9” x 9” x 18”) blocks shall be used for the construction of all substructures while 150mm x 225mm x 450mm (6” x 9” x 18”) blocks are to be used for construction of superstructure.  All substructure walls must be filled with weak concrete unless otherwise is stated.

Construct walling with all materials fully bonded or tied together to ensure compliance with design requirements for stability, strength, fire resistance and thermal as relevant.

Lay blocks on full bed or mortar with joints filled to consistent thickness of not more than 12mm.

Submit samples of each type of block and obtain approval from the Employer/Engineer before placing orders.

Provide coping 250mm wide and 50mm thick with spikes on top of all exposed walls as approved by the engineer

Storing – stack blocks so that they are stable and clear of the ground.  Protect from inclement weather.

## 5.1.13	Water

The water used for mixing and curing should be clean and free from injurious quantities of alkalis, acid, oils, salt, sugar, organic materials, vegetable growth and other substances that may be deleterious to bricks, stone, concrete or steel. Potable water is generally considered satisfactory for mixing. The pH value of water should be not less than 6.

## 5.1.14	Roofing

All timber used for permanent works shall be the best of its kind approved by the Engineer as suitable for the particular purpose, and it shall in all cases be thoroughly seasoned sound, dry, straight and free from sap, shakes, dead knots, dog marks or other defects, and shall be sawn into scantlings of the requisite dimensions not less than one month before use, and in the case of joinery not less than three months before use.  Only unused timber shall be incorporated into the works.

All timber must be treated with Solignum or any other approved anti- termite solutions before installation.

In case of lapping or joining, all lap lengths must be at least 600mm.

Engineer approved 0.45mm aluminum roofing sheet shall be laid at 150mm and double lapping nailed to purlin.

## 5.1.15	Metal work and Joinery

The work required under this section includes doors, rails etc. in building

The contractor shall supply all the, metal, paints and auxiliary materials required, shall install them in the required positions and paint them- all in accordance with the drawings, BOQ and specification, or as directed by the engineer.

Note: All metal works must be coated 3 times with anti-rust before finishing with gloss. In case of doors, they should be treated with anti – rust before hanging in place.

## 5.1.16	Plumbing and accessories

The contractor shall prepare and submit to the engineer drawing showing the general arrangement of all piping for approval, before ordering for the materials.

All plumbing works should be conduit.

All pipes should be at least 4bar and engineer approved adhesive should be used.

All exposed waste pipes must be covered with floor drain

All wash hand basins are to be of approved ceramic type embedded in concrete and shall contain opening to serve as service access. The wash hand basins shall not contain bottle traps or flexible waste pipes but shall rather open into 2” pipe which will empty into the urinal pipe. The water from hand washing is to flush the urinals as such a reasonable slope shall be maintained to accomplish this.

All taps to be used should be “two turn” valve.

The hand washing facility (tank) should be embedded in concrete and must be black in colour with configuration as in the drawing or as directed by the engineer

## 5.1.16.1	Fixtures

A.	Service sinks or wash hand basins

All wash hand basins shall be ceramic, with single bowl, white in color and should be embedded in block wall as directed by the engineer and should have access for servicing provided. All the tap fittings should be provided, and the tap fixed 12.5mm flexible connector. The basin is placed directly over a 50mm waste pipe.

B.	Urinals

For females, a concrete purpose made urinal trough finished with vitrified tiles shall be used as directed by the engineer.

The male block shall comprise of a drain partitioned at given intervals and finished with tiles as directed by the engineer.

Note that all the urinals are connected to discharge into a soak pit.

C.	Squatting pan

All squatting pan shall contain U-trap and shall be of good quality. The pans with footrest or tread are preferred. The squatting pans should flush with the finished (tiled) floor with the floor cambering (sloping) to the pan.

D.	Accessories

Each compartment of the female block should be provided with kettle, bucket, and waste bin. Whereas the male block compartments shall have only bucket and kettle. Note that the waste bins shall have lid.

## 5.1.17	Ventilation

The screen wall should contain perforated blocks (fancy blocks) covering at least 450mm height as shown in the drawing or as directed by the engineer.

Each compartment shall contain at least 1 perforated block on the back wall to serve as ventilation space.

All doors shall be perforated as shown in the drawing

## 5.1.18	Painting and Decoration

All external walls shall be finished with deep green Sandblasting leaving out the area for art work or as directed by the Engineer

All internal walls shall be finished with cream color emulsion paint (approved by the Engineer).

Metal works shall contain 3 coats anti-rust finished with rich/dirty brown color gloss.

All fascia board shall be covered with flat pan.

All wet areas must be tiled as directed. All tiles to be used must be approved by the engineer and should be white in color (or as approved by the engineer). For all platforms serving as tread, rough or friction surface floor tiles shall be used to reduce the risk of slipping.

## 5.1.19	Physically Challenged Aids

The compartment for the physically challenged should have the following:

- A ramp of slope 1:10

- The sitting type WC to replace the squatting pan

- Handrail made of 25mm diameter thick gauge galvanized pipe or any other material approved by the engineer

- The door should be wider (at least 800mm)

- Ramp on all the entrance to the facility. (The slope of all ramps should be 1:10)

## 5.1.20	Artwork

Some simple hygiene education messages are to be inscribed on the walls of the latrines after construction. The latrine block should have the following messages.

- Keep your toilet clean always.

- Prevent diseases, use sanitary latrine.

- Wash your hands with soap after using toilet.

The water tank should bear an inscription showing the owners of the project.

The above messages could be translated into local languages. The translation would be done by the Employer/Engineer in conjunction with the contractor and the community.

## 5.1.21	Inspection of construction

To ensure that the construction is in accordance with the design, an inspection procedure should be set up covering materials, records, workmanship, and construction.

Tests should be made on the constituent materials of reinforced concrete in accordance with the relevant standards; the production and testing of concrete should conform to BS 5328. Where applicable, use should be made of suitable quality assurance schemes.

The Employer shall be responsible for the cost of supervision of latrine construction in selected locations.

## 5.1.22	Cleaning of Building and Handing Over

On completion, the buildings shall be handed over by the Contractor to the Engineer in a perfectly clean condition.  Floors, walls woodwork and metalwork shall be free for use.

The surroundings must be cleaned of all rubbles and rubbish arising from construction and the surrounding earth leveled as directed by the engineer. The cost of cleaning shall be spread over all items of building work in the Bill of Quantities.

The completed latrine should be locked and handed over to the authority of the beneficiary institution with the authorization of the Employer.

# 5.2.0	DESIGN CHOICE CRITERIA.

## 5.2.1	Earthworks

Excavation works are to be manually accomplished. Mechanical excavation, results in higher costs and vibration of earth; which are not desirable for this work.

Shovels and hand diggers are therefore of choice; using unskilled labour which is readily available in the community.

## 5.2.2	Concrete Work

Designs are in mandatory professional compliance of BS8110; Regulating structural use of concrete.

Design mixes are as regulated in the Building Regulations 1985.

Cements that satisfy the requirements for Portland cement, are commonly available nationwide, hence of choice.

Mechanical mixing is usually obtainable at higher costs. It is therefore not desirable within the scope of this work. The volume of concrete works here are minor. Shovels, head pans, wheelbarrows, are therefore of choice using semi-skilled and skilled manpower.

## 5.2.3 	POUR FLUSH 2&4-COMPARTMENT LATRINE

Pour flush 3-compartment latrine is a conventional sanitation facility that is water driven for operation. It is more suitable where there is adequate water supply to operate and maintain the system. Pour flush 3-Compartment latrines are suitable for small households/ communities. Human Wastes are evacuated from time to time from the septic tank.

# 5.3.0	OPERATION & MAINTENANCE SCHEDULE

Operation and maintenance protocols for WASH facilities

O & M REQUIREMENTS FOR POUR FLUSH

| Activity | Frequency | Human Resources | Materials and Spare Parts | Tools and Equipment |
| --- | --- | --- | --- | --- |
| Ensure cleaning of all surfaces including floor and building | Daily | Environmental Health Clubs(EHC)/school authorities | Detergents, disinfectants, soaps | Brush, broom, mop, cutlass |
| Repair building | Occasionally | PTA/SBMC | Cement, sand, nails, screen net, taps, local building materials | Bucket, trowel, saw, hammer, knife. |

Person& skills required in O&M for Pour Flush

| Persons | Role | Skills |
| --- | --- | --- |
| Users | Tidy up the toilet environment | Understanding of hygiene |
| WASHCOM | Collect user fees, keep facilities clean, | Understanding of hygiene and hygiene promotion, |
| Sanitation service | Repair if needed | Basic masonry, skills to work with vacuum tanker. |

Technical drawings and sketches

See attached Annex 1

# Sample Contract

This is the anticipated contract. However, if required, additional terms and conditions may be added by Mercy Corps in the final contract.

INTERMEDIATE WORKS CONTRACT

Contract No. ______

THIS WORKS CONTRACT entered into as of _______________ by and between MERCY CORPS, a State of Washington, U.S.A. nonprofit corporation having its principal office in Portland, Oregon, U.S.A. (“Mercy Corps” or “MC”), and _____________________________ (“Contractor”) is as follows

- Additional Terms and Defined Terms.   Additional Terms are specified in Schedule I hereto (the “Additional Terms”).  The terms in Schedule I are incorporated in this Contract by this reference.  The following additional defined terms are included in Schedule I: Authorized Representative, Owner, Payment Terms and Subcontractor Percentage Limit.  “Contract” means this Works Contract as amended, modified or supplemented from time to time together with its Schedules and appendixes (if any).  “Statement of Work” means the Statement of Work attached as Schedule II. “Work” or “Works” means all the goods and services described in the Statement of Work.  Other terms may be defined throughout this Contract as specified.

- The Work.  Contractor, together with its Subcontractors (if any), will fully execute and complete the Work in accordance with the terms and conditions set forth in this Contract.  The Contractor will perform and complete the Work strictly in accordance with this Contract.  Contractor warrants that all Work will be completed in strict adherence to the approved design and engineering plans, any relevant government issued permits and authorizations, and any Mercy Corps approved Bills of Quantity as applicable per the Statement of Work collectively the “Specifications”).  Each Statement of Work will list out the documents that will be used as the Specifications.  No deviation, substitution or change is permitted without Mercy Corps’ prior written consent following the Change Order processes required in this Contract.

- Subcontractors.

  - Contractor is only allowed to subcontract components of the work if Schedule I indicates that subcontracting is allowed.  “Subcontractor” means a person or entity that has a direct contract with Contractor (or with another Subcontractor) to perform a portion of the Work or to supply materials or equipment for the Work.  “Subcontract” means an agreement between Contractor and a subcontractor.

  - Even when allowed, Contractor must notify in writing MC’s Authorized Representative in advance of any subcontractor it intends to hire.  MC’s authorized representative may reject any subcontractor if MC has reasonable grounds to believe that the subcontractor is not qualified to perform the work, is charging more than the market rate or would violate any of the warranties and representations in this Contract.  In no event will Contractor be reimbursed or paid by Mercy Corps for any amounts paid or owed to subcontractors that exceeds the Subcontracting Percentage Limit in Schedule I.

  - Contractor will be solely responsible, and Mercy Corps will not have responsibility, for all aspects of safety related to the Work.  Contractor will take all necessary precautions for the safety of, and will provide protection to prevent damage, injury or loss to, persons or property whether it be their own, Mercy Corps’ or community.

# SCHEDULE III. Other Contract Provisions Required by Law or MC’s Donor

A: DFID funded Program

Mercy Corps, in accordance with donor regulations, requires certain certifications and provisions, set forth herein, to be included in all contracts.

Liability/Indemnity

The Contractor acknowledges that DFID will not be held responsible for or in relation to the activities of the Contractor under this Contract.

Right of Access/ Audit

The Contractor shall permit Mercy Corps, its donor, DFID (UK), and/or the UK’s National Audit Office and/or any of their duly authorized representatives, access to project sites and relevant records, including books, documents, papers (including in electronic format) for the purpose of monitoring, evaluation and audit.    Such verification or audit may take place at any time during this Contract and up to seven years after final payment made under this Contract.

Anti-Corruption and Anti-Bribery

The parties recognize that Mercy Corps has a zero-tolerance approach to bribery and corruption.  The Contractor will comply with all relevant anti-bribery and anti-corruption laws (including the UK Bribery Act 2010) and comply with the principles of Mercy Corps’ Anti-Corruption and Anti-Bribery Policies, or equivalent policies, including: (a) not accepting or offering a bribe of facilitation payment; and (b) reporting immediately to Mercy Corps any bribery issues which the Contractor becomes aware of during this Contract; and, at the reasonable request of Mercy Corps, confirming in writing that they have complied with this clause and provide any information reasonably requested in support of such compliance. MC recognizes that in complying with this clause, the Contractor is not expected to risk life, limb or freedom.

Cancelation of the Contract

If any illegal or corrupt practices were or are committed in the award or execution of this Contract, including if any offer, gift, payment, contribution or benefit of any kind was accepted as an inducement or reward for the award or execution of this Contract, this Contract will be cancelled with immediate effect, in which case Mercy Corps will return to the Contractor any items delivered and the Contractor will return to Mercy Corps any funds paid (at each of their own cost, unless otherwise agreed).

Confidentiality

The Contractor acknowledges that Mercy Corps has reporting obligations to DFID.  Accordingly, the Contractor consents to Mercy Corps sharing information about the Vendor or the Services with DFID as required.

Conflict of Interest

- The Vendor shall take all reasonable precautions to avoid any conflict of interests and shall inform MC without delay of any situation constituting or likely to entail a conflict of interests.

- There is a conflict of interests where the impartial and objective exercise of the functions, tasks and activities under this Contract is compromised for reasons involving family, emotional life, political or national affinity, economic interest or any other shared interest with another person or party.

Principal of Ethical Procurement

The Contractor acknowledges that Mercy Corps must comply with DFID’s principle of Ethical Procurement including adhering to the minimum ethical standards of the avoidance of child labour, and the respect of basic social rights and working conditions based on international labour standards.

Child Protection

The Contractor acknowledges that, under the Donor Contract, the recipients of funds are required to have a robust child protection policy and mechanisms to monitor its adherence and that it is important that a focus on child protection is maintained throughout the lifecycle of the Project.  The Donor reserves the right to ask for the relevant child protection policy and mechanisms and test that they are implemented during the life of the Project.

B: DOS funded Program

Mercy Corps, in accordance with donor regulations, requires certain certifications and provisions, set forth herein, to be included in all contracts.

- The Contractor is reminded that U.S. Executive Orders and U.S. law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism. It is the legal responsibility of the Contractor to ensure compliance with these Executive Orders and laws.

- Contractor certifies that neither it nor its principals is presently excluded or disqualified from participation in this transaction by any US Government department or agency.

- Contractor certifies that it will not and has not used any funds received directly or indirectly from the U.S. Government has been paid or will be paid to any person or organization for influencing or attempting to influence an officer or employee of any agency, a member of U.S. Congress, officer or employee of Congress, or an employee of a member of Congress in connection with obtaining this Contract or any other U.S. government funded project.

- Mercy Corps, the US Department of State, the Inspector General of the United States, and the Comptroller General of the United States, or any of their duly authorized representatives have the right of timely and unrestricted access to any books, documents, papers and records of Contractor that are pertinent to this Contract, in order to make audits, examinations, excerpts and transcripts and copies of such documents. This right also includes timely and reasonable access to a Contractor’s personnel for the purpose of interview and discussion related to such documents.

- The U.S. Government is opposed to prostitution and related activities, which are inherently harmful and dehumanizing, and contribute to the phenomenon of trafficking in persons. None of the funds made available under this contract may be used to promote, support, or advocate for the legalization or practice of prostitution. Nothing in the preceding sentence shall be construed to preclude assistance designed to ameliorate the suffering of, or health risks to, victims while they are being trafficked or after they are out of the situation that resulted from such victims being trafficked. The Contractor does not promote, support, or advocate the legalization or practice of prostitution.

- Mercy Corps has the right to terminate this Contract, without penalty, if Contractor or its employees, or any Subcontractor or its employees, engage in any of the following conduct:

- Trafficking in persons (as defined in the Protocol to Prevent, Suppress, and Punish Trafficking in Persons, especially Women and Children, supplementing the UN Convention against Transnational Organized Crime) during the period of this Contract;

- Procure a commercial sex act during the period of time that this Contract is in effect; or

- Use forced labor in the performance of the Contract.

- The Contractor agrees to incorporate the terms of “Exhibit C” word-for-word in all of its sub-contracts funded under this Contract, if any.

C: European Funded Programs

Mercy Corps has received funding from European Union, designated herewith as the Donor. Mercy Corps, in accordance with the Donor regulations under which this contract is executed, requires certain certifications and provisions, set forth herein, to be included in all contracts.

Liability/Indemnity

Under no circumstances nor for any reason whatsoever will the Donor be held liable for damages as a result of the work pursuant to this Contract.

Right of Access/ Audit

- The Contractor will be responsible for holding all invoices, receipts and financial and accounting documents relating to this Contract for at least seven years following final payment made under this Contract.

- The Contractor will allow Mercy Corps or the Donor (or any other organisation authorised by the Donor) access to the location where the Contractor is based or any location where the Services are being implemented and to all documents, information and other material related to this Contract (including in electronic format), necessary to assess, or audit the implementation of the project and compliance with this Contract.   Such audit may take place at any time during this Contract and up to seven years following final payment made under this Contract.

Confidentiality

The Contractor acknowledges that Mercy Corps has reporting obligations to the Donor.  Accordingly, the Contractor consents to Mercy Corps sharing information about the Contractor or the Services with the Donor as required.

Anti-corruption

The Parties recognize that Mercy Corps has a zero tolerance approach to bribery and corruption.  The Contractor will comply with all relevant anti-bribery and anti-corruption laws (including the UK Bribery Act 2010) and comply with the principles of Mercy Corps’ Anti-Corruption and Anti-Bribery Policies, or equivalent policies, including: (a) not accepting or offering a bribe of facilitation payment; and (b) reporting immediately to Mercy Corps any bribery issues which the Contractor becomes aware of during this Contract; and, at the reasonable request of Mercy Corps, confirming in writing that they have complied with this Clause and provide any information reasonably requested in support of such compliance.

Mercy Corps recognizes that in complying with this Clause, the Contractor is not expected to risk life, limb or freedom.

Principal of Ethical Procurement

The Contractor acknowledges that Mercy Corps must comply with the Donor’s principle of Ethical Procurement including adhering to the minimum ethical standards of the avoidance of child labour, and the respect of basic social rights and working conditions based on international labour standards.

D: USAID Funded Programs

Mercy Corps, in accordance with donor regulations, requires certain certifications and provisions, set forth herein, to be included in all contracts.

- The recipient must not engage in transactions with, or provide resources or support to, individuals and organizations associated with terrorism, including those individuals or entities that appear on the Specially Designated Nationals and Blocked Persons List maintained by the U.S. Treasury (online at: http://www.treasury.gov/resource-center/sanctions/SDNList/Pages/default.aspx) or the United Nations Security designation list (online at: http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml).

- Contractor certifies that neither it nor its principals is presently excluded or disqualified from participation in this transaction by any US Government department or agency.

- Contractor certifies that it will not and has not used any funds received directly or indirectly from the U.S. Government to pay any person or organization for influencing or attempting to influence an officer or employee of any agency, a member of U.S. Congress, officer or employee of Congress, or an employee of a member of Congress in connection with obtaining this Contract or any other U.S. government funded project.

- Mercy Corps, USAID, and the Comptroller General of the United States, or any of their duly authorized representatives, shall have access to any books, documents, papers and records of Contractor which are directly pertinent to this Contract for the purpose of making audits, examinations, excerpts and transcriptions.

- The Contractor or its employees, or any Subcontractor or its employees, must not engage in any of the following conduct:

(i) Trafficking in persons (as defined in the Protocol to Prevent, Suppress, and Punish Trafficking in Persons, especially Women and Children, supplementing the UN Convention against Transnational Organized Crime) during the period of this Contract;

(ii) Procure a commercial sex act during the period of this Contract;

(iii) Use forced labor in the performance of the Contract; or

(iv) Commit acts that directly support or advance trafficking in persons, including the following acts:

a. Destroying, concealing, confiscating, or otherwise denying an employee access to that employee's identity or immigration documents;

b. Failing to provide return transportation or pay for return transportation costs to an employee from a country outside the United States to the country from which the employee was recruited upon the end of employment if requested by the employee, unless:

- exempted from the requirement to provide or pay for such return transportation by Mercy Corps under this award; or

- the employee is a victim of human trafficking seeking victim services or legal redress in the country of employment or a witness in a human trafficking enforcement action;

c. Soliciting a person for the purpose of employment, or offering employment, by means of materially false or fraudulent pretenses, representations, or promises regarding that employment;

d. Charging employees’ recruitment fees; or

e. Providing or arranging housing that fails to meet the host country housing and safety standards.

The Contractor agrees to report in a timely manner to Mercy Corps any credible information from any source that alleges the contractor or any sub-contractor has engaged in any of the prohibited activities identified in this provision.

- The Contractor must inform its employees working under this contract in the predominant native language of the workforce that they are afforded the employee whistleblower rights and protections provided under 41 U.S.C. § 4712; and

- Prohibition on Requiring Certain Internal Confidentiality Agreements or Statements

        - The Contractor must not require its employees or sub-contractors to sign or comply with internal confidentiality agreements or statements that prohibit or otherwise restrict employees or sub-contractors from lawfully reporting waste, fraud, or abuse related to the performance of this contract to Mercy Corps or to USAID’s Office of the Inspector General.

        - The Contractor must notify current employees and sub-contractors that prohibitions and restrictions of any preexisting internal confidentiality agreements or statements covered by this provision, to the extent that such prohibitions and restrictions are inconsistent with the prohibitions of this provision, are no longer in effect.

        - If Mercy Corps, USAID or other authorized officials of the US Government determines that the Contractor is not in compliance with the requirements of this provision, Mercy Corps may, at its sole discretion, suspend or terminate the contract.  Further, Mercy Corps may, at its sole discretion, decide not pay a portion or all of amounts invoiced or expenditures incurred, as applicable, by the Contractor with funds provided under this contract, and also may require the Contractor to refund a portion or all of any amounts paid to the Contractor under this contract.

        - Definitions:

Terms in this clause will have the meaning defined in this section or as defined in 2 CFR 200.

“Internal confidentiality agreement or statement” means a confidentiality agreement or any other written statement that the Contractor requires any of its employees or sub-contractors to sign regarding nondisclosure of recipient information, except that it does not include confidentiality agreements arising out of civil litigation or confidentiality agreements that Contractor employees or sub-contractors sign at the behest of a US government agency.

        - The Contractor must include this provision, including this paragraph (e), in subawards and sub-contracts funded under this contract.

- Contractor must disclose, in a timely manner, in writing to the USAID Office of Inspector General and Mercy Corps all violations of US government criminal law involving fraud, bribery or gratuity violations potentially affecting this Contract.

Disclosures to USAID must be sent to:

U.S. Agency for International Development

Office of the Inspector General

P.O. Box 657

Washington, DC 200044-0657

Phone: 1-800-230-6539 or 202-712-1023

Email: ig.hotline@usaid.gov

URL: https://oig.usaid.gov/content/usaid-contractor-reporting-form

- USAID policy requires that the contractor not discriminate against any beneficiaries in implementation of this contract, such as, but not limited to, by withholding, adversely impacting, or denying equitable access to the benefits provided through this contract on the basis of any factor not expressly stated in the contract. This includes, for example, race, color, religion, sex (including gender identity, sexual orientation, and pregnancy), national origin, disability, age, genetic information, marital status, parental status, political affiliation, or veteran's status. Nothing in this provision is intended to limit the ability of the contractor to target activities toward the assistance needs of certain populations as defined in the contract.

- The Contractor agrees to incorporate the terms of “Schedule II – subsection C” word-for-word in all of its sub-contracts funded under this Contract, if any.

E. Reporting of currency and cash-based transaction required under Nigerian laws.

- The special control unit against money laundering (SCUML) as well as Federal Ministry of Industry, trade and investment, in line with the provision of the “Money Laundering

(Prohibition) Act (TPA)” 2011 (as amended) and Federal Ministry of Industry, Trade and Investment (designation of Non-Financial institutions) 2013 and 2016 respectively, requires designated non-financial institutions to report all currency transactions of N5,000,000 and above, in case of an individual or N10,000,000 and above, in the case of a body corporate within seven (7) days from the date of transaction.

- The laws also require designated non-financial institutions to report all cash-based transactions in excess of $1,000 or its equivalent within seven (7) days to SCUML through its online platform.

- Accordingly, Mercy Corps, being a registered and designated non-financial institution, in compliance with above requirements in clause a and b of this document is obliged to report all transaction to SCUML.

- By signing this document, the vendor/contractor/service provider unconditionally allows Mercy Corps to share necessary data and documents with SCUML and the “Economic and Financial Crimes Commission (EFCC).

- Vendor/contractor/service provider also agrees to allow SCUML and EFCC the unconditional access to his bank account(s), account books and daily ledger with regard to the amount paid against this contract.

# Attachments to the Tender Package

  - Attachment 1 -Supplier Information Form.

This document must be submitted with your bid

The information provided will be used to evaluate the Company before contracting with the Mercy Corps.

Please complete all fields.

Supplier Information

| Company Name |  |
| --- | --- |
| Any other names company is operating under (Acronyms, Abbreviations, Aliases) |  |
| Previous names of the company |  |
| Address |  |
| Website |  |
| Phone/Fax Numbers | Phone: Fax: |
| Primary Contact | Name: Phone Number: Email Address: |
| Government - owned (yes/no) |  |
| Name(s) of Board of Directors |  |
| Name(s) of Company Owner(s) |  |
| Parent companies, if any |  |
| Subsidiary or affiliate companies, if any |  |
| Vendor Capacity |  |
| Number of qualified Staff. |  |
| Do you operate in Borno State or the Northeast Nigeria? |  |
| Do you operate in the Deep Field Locations within Borno State e.g. Shani & Biu LGAs? |  |
| Do you have experience in Construction of Toilets / Latrines? If yes, attach similar contract(s) successfully completed with evidence of works completion |  |
| Do you have the equipment and the relevant personal to deliver works? If Yes, attach CVs of relevant personal and evidence of equipment ownership or least agreement |  |
| Vendor Experience: |  |
| What is your primary area of business? |  |
| How many years of experience do you have in this field? |  |
| Provide examples of similar work executed i.e. Contracts or service completion certificates from INGO, UN or government agencies |  |
| Please mention previous similar works done. (attach contract if possible) | 1. 2. 3. |
| Will you subcontract other companies for the project? |  |
| Other: |  |
| Do you understand the security situation between these routes? Shani & Biu LGAs – Borno State. |  |
| Can you get approval from Authorities to move equipment and personal to deliver works in Shani & Biu LGAs? Please attach acknowledgement. |  |

Financial Information

| Bank Name and Address |  |
| --- | --- |
| Bank Account Number |  |
| Name under which company is registered at bank |  |
| Payment Terms: Payment will be done in wire transfer. |  |
| MC will do the payment after the completion of works; do you agree on these terms? |  |
| Payment will be based on deliverable and invoice will only be paid after the completion of each deliverable |  |

Delivery Time/Completion Time

| How many days, from the time of contract signature will it take you to mobilize to site, commence work, complete the entire works and handover projects to Mercy Corps? |  |
| --- | --- |

References

This information is required; references should be a former client whom the company have rendered similar service(s)

| Client Name: | - Contact Name, Phone, Email Address: |
| --- | --- |
| Client Name: | - Contact Name, Phone, Email Address: |
| Client Name: | - Contact Name, Phone, Email Address: |

Supplier Self-Certification of Eligibility

Company certifies that:

- It, its affiliates and subsidiaries, owners, officers, directors and key employees (to the best of its knowledge) are not the subject of any government’s sanctions, designations, donor rules or prohibitions, or laws prohibiting transactions with it/them. It is not the subject of any donor government investigation into its misconduct with any other recipient of that donors funding.

- It, its affiliates and subsidiaries, owners, officers, directors and key employees have not and do not engage in any form of terrorism or attacks on civilians and do not provide any form of material support or financial resources for individuals or organizations that do engage in any form of terrorism or deliberate attacks on civilians.

- It, its affiliates and subsidiaries, owners, officers, directors and key employees have not and do not engage in weapons or drugs manufacture, transport, sale or distribution.

- It is not in default on any material credit agreement, bankrupt or being wound up, are having its affairs administered by the courts, have entered into arrangements with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations.

- It is has not been determined to be in breach of a material contract by any legal body anytime within the past 2 years.

- It pays taxes as and when due and is not currently the subject of any investigation or proceeding related to back-owed taxes.

- It provides workers compensation insurance to its workers in accordance with the laws of the countries where it operates.

- It pays social security obligations as required in the countries where it operates.

- It, its owners, officers and directors have not been convicted of an offense concerning its professional conduct and has not engaged in grave professional misconduct.

- It, its affiliates and subsidiaries, owners, officers, directors and key employees have not been the subject of criminal investigation or judgement for fraud, corruption, human trafficking, spying, weapons transport or smuggling, sexual exploitation or abuse, involvement in a criminal organization or any other criminal activity.

- It treats its employees with dignity and respect and maintains social operating standards, including:  working conditions and social rights: avoidance of child labor, bondage, forced labor, human trafficking or exploitation; assurance of safe and reasonable working conditions; freedom of association; freedom from exploitation, abuse, and discrimination; protection of basic social rights of its employees and Mercy Corps beneficiaries.

- To the best of its knowledge, no Mercy Corps employee, officer, consultant or other party related to Mercy Corps has a financial interest in the Company’s business activities, nor is any Mercy Corps employee related to any owner, officer, director or employee of the company, and, if so, it will ensure that the relationship is disclosed to Mercy Corps and will not used for improper influence.  Discovery of an undisclosed Conflict of Interest will result in immediate revocation of the Company’s Authorized Supplier status and disqualification of Company from participation in future Mercy Corps procurement.

- It understands that attempting to or agreeing to provide anything of value to any Mercy Corps employee, agent or representative for the purpose of encouraging that person to award Company a contract or take or not take any action related to any contract will result in immediate termination of any agreement.  Company certifies that it does not engage in such conduct.

- It understands that Mercy Corps seeks fair and open competition and the fairest price available and that any attempt by company to subvert fair and open competition, including working with other bidders to fix prices, working to exclude competition, seeking confidential information from Mercy Corps or other bidders, using multiple related or controlled companies to give the appearance of competition, or any similar activity, will result in termination of any agreement.  Company certifies that it does not engage in such conduct.

- It understands that Mercy Corps prohibits any of its partners or suppliers from bribing public officials and certifies that it does not do so.

- It is not conducting business under other names or aliases that have not been declared to Mercy Corps.

If the Company cannot certify to any of the above, it should explain why not.  Mercy Corps may take the individual circumstances into account for some situations. However, any false certification could be grounds for immediate disqualification and termination of any future agreement.

By signing the Supplier Information Form, you certify that your Company is eligible to supply goods and services to major donor funded organizations and that all of the above statements are accurate and factual.

Company Name:

Name of Representative:

Title:

Signature:

Date:

MERCY CORPS USE ONLY

Following documents have been provided:

| Documents |  |
| --- | --- |

I ________________________ an employee of Mercy Corps having completed and reviewed this form confirm the accuracy of information provided:

Name		______________________________

Title		______________________________

Signature	______________________________

Date*		______________________________

  - Attachment 2 - Price Offer Sheets

| BILL OF QUANTITIES FOR SANITATION FACILITIES - MOTOR PARK SHANI |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| (4Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel |  | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 25.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 25.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 1.43 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 17.50 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 10.60 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.07 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 34.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 7.20 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 6.00 | m |  |  |
| C | 50 X 50mm Purlins | 14.00 | m |  |  |
| D | 50 X 100mm wall plate | 7.20 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 11.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 4.00 | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 2.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 4.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 4.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 4.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 2.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 2.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 2.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 2.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.81 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 4.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 70.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 14.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 6.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 20.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for artwork) as specified in the or directed by the Engineer | 24.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 litres) | 3.00 | No |  |  |
| B | Provision of Kettle for the toilet | 3.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 4950mm x 3675mm x2050mm) |  |  |  |  |
| A | Exacavtion of pit size 5400mmx 4125mm x 1825mm | 41.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 4.10 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.09 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 2.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 1.70 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.25 | m3 |  |  |
| G | 225mm sandcrete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 35.20 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 35.20 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 30.00 | m3 |  |  |
| K | 225mm thick hollow sancrete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 18.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 18.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – MAIN MARKET SHANI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (2Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel | 1 | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 10.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 15.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.45 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 9.00 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 5.20 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.05 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 20.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 4.00 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 4.00 | m |  |  |
| C | 50 X 50mm Purlins | 8.00 | m |  |  |
| D | 50 X 100mm wall plate | 4.00 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 6.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 2.00 | No |  |  |
| B | Supply and fix purpose made 800mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings |  | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 1.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 2.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 2.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 2.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 1.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 1.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 1.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 1.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.50 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 2.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 37.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 8.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 3.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 12.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for art work) as specified in the or directed by the Engineer | 14.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 liters) | 2.00 | No |  |  |
| B | Provision of Kettle for the toilet | 2.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 3500mm x 2500mm x1750mm) |  |  |  |  |
| A | Excavation of pit size 3750mmx 2850mm x 1500mm | 17.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 1.70 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.04 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 1.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.90 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.17 | m3 |  |  |
| G | 225mm sand Crete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 15.40 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 15.40 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 15.00 | m3 |  |  |
| K | 225mm thick hollow sand Crete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 8.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 8.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |
|  | GRAND TOTAL |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – GOVT SEC SCH SHANI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (2Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel | 1 | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 10.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 15.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.45 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 9.00 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 5.20 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.05 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 20.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 4.00 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 4.00 | m |  |  |
| C | 50 X 50mm Purlins | 8.00 | m |  |  |
| D | 50 X 100mm wall plate | 4.00 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 6.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 2.00 | No |  |  |
| B | Supply and fix purpose made 800mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings |  | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 1.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 2.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 2.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 2.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 1.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 1.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 1.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 1.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.50 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 2.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 37.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 8.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 3.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 12.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for art work) as specified in the or directed by the Engineer | 14.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 liters) | 2.00 | No |  |  |
| B | Provision of Kettle for the toilet | 2.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 3500mm x 2500mm x1750mm) |  |  |  |  |
| A | Excavation of pit size 3750mmx 2850mm x 1500mm | 17.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 1.70 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.04 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 1.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.90 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.17 | m3 |  |  |
| G | 225mm sand Crete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 15.40 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 15.40 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 15.00 | m3 |  |  |
| K | 225mm thick hollow sand Crete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 8.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 8.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |
|  | GRAND TOTAL |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – BIGARU SCH SHANI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (2Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel | 1 | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 10.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 15.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.45 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 9.00 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 5.20 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.05 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 20.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 4.00 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 4.00 | m |  |  |
| C | 50 X 50mm Purlins | 8.00 | m |  |  |
| D | 50 X 100mm wall plate | 4.00 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 6.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 2.00 | No |  |  |
| B | Supply and fix purpose made 800mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings |  | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 1.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 2.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 2.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 2.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 1.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 1.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 1.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 1.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.50 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 2.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 37.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 8.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 3.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 12.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for art work) as specified in the or directed by the Engineer | 14.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 liters) | 2.00 | No |  |  |
| B | Provision of Kettle for the toilet | 2.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 3500mm x 2500mm x1750mm) |  |  |  |  |
| A | Excavation of pit size 3750mmx 2850mm x 1500mm | 17.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 1.70 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.04 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 1.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.90 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.17 | m3 |  |  |
| G | 225mm sand Crete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 15.40 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 15.40 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 15.00 | m3 |  |  |
| K | 225mm thick hollow sand Crete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 8.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 8.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |
|  | GRAND TOTAL |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – GAMJI PRI SCH |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| (4Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel |  | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 25.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 25.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 1.43 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 17.50 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 10.60 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.07 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 34.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 7.20 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 6.00 | m |  |  |
| C | 50 X 50mm Purlins | 14.00 | m |  |  |
| D | 50 X 100mm wall plate | 7.20 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 11.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 4.00 | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 2.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 4.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 4.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 4.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 2.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 2.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 2.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 2.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.81 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 4.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 70.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 14.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 6.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 20.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for artwork) as specified in the or directed by the Engineer | 24.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 litres) | 3.00 | No |  |  |
| B | Provision of Kettle for the toilet | 3.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 4950mm x 3675mm x2050mm) |  |  |  |  |
| A | Exacavtion of pit size 5400mmx 4125mm x 1825mm | 41.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 4.10 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.09 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 2.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 1.70 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.25 | m3 |  |  |
| G | 225mm sandcrete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 35.20 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 35.20 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 30.00 | m3 |  |  |
| K | 225mm thick hollow sancrete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 18.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 18.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – UBE SCH FILIN JIRGI BIU |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| (4Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel |  | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 25.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 25.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 1.43 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 17.50 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 10.60 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.07 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 34.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 7.20 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 6.00 | m |  |  |
| C | 50 X 50mm Purlins | 14.00 | m |  |  |
| D | 50 X 100mm wall plate | 7.20 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 11.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 4.00 | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 2.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 4.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 4.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 4.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 2.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 2.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 2.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 2.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.81 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 4.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 70.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 14.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 6.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 20.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for artwork) as specified in the or directed by the Engineer | 24.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 litres) | 3.00 | No |  |  |
| B | Provision of Kettle for the toilet | 3.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 4950mm x 3675mm x2050mm) |  |  |  |  |
| A | Exacavtion of pit size 5400mmx 4125mm x 1825mm | 41.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 4.10 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.09 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 2.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 1.70 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.25 | m3 |  |  |
| G | 225mm sandcrete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 35.20 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 35.20 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 30.00 | m3 |  |  |
| K | 225mm thick hollow sancrete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 18.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 18.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |

| BILL OF QUANTITIES FOR SANITATION FACILITIES – GSSS BIU |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (2Nos COMPARTMENT POUR FLUSH LATRINE) |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
|  | PRELIMINARIES AND GENERAL ITEMS |  |  |  |  |
| A | Inter-site Mobilization and Demobilization of equipment and personnel | 1 | LS |  |  |
|  | SUBSTRUCTURE |  |  |  |  |
| A | Clearing of Site | 10.00 | m2 |  |  |
| B | Excavate trenches, 525mm width and 600mm depth to receive foundations starting from the strip level | 6.00 | m3 |  |  |
| C | Provide approved anti termite treatment to surfaces of excavation | 15.00 | m2 |  |  |
|  | CONCRETE WORKS |  |  |  |  |
| A | Strip footing (Plain insitu concrete 1:2:4 mix) | 1.00 | m3 |  |  |
| B | Floor slab 150mm thick (Plain in situ concrete 1:2:4 mix, 20mm aggr.) | 0.80 | m3 |  |  |
| C | 100mm thick slab on corridor (Plain in situ concrete mix (1:2:4 mix, 20mm aggr.) | 0.45 | m3 |  |  |
| D | Formwork (Ditto edges of bed not exceeding 150mm high) | 9.00 | m2 |  |  |
|  | Blockwork |  |  |  |  |
| A | 225mm thick sand Crete hollow block filled with solid weak concrete in foundation | 5.20 | m2 |  |  |
|  | Substructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | SUPERSTRUCTURE |  |  |  |  |
|  | Concrete Works |  |  |  |  |
| A | Provide 250mmx50mm thick coping with spikes on top of all exposed walls as approved by the engineer | 0.05 | m3 |  |  |
|  | External and Internal Wall |  |  |  |  |
| A | Blockwork 150mm sand Crete block laid in cement and sand (1:4) to wall plate including urinal partitions | 20.00 | m2 |  |  |
|  | Roofing /Carpentry |  |  |  |  |
|  | 0.45mm thick long span aluminum roofing sheet laid at 150mm and double nailed to purlin (measured separately) |  |  |  |  |
| A | Roofing (complete with all accessories) | 4.00 | m2 |  |  |
|  | (Solignum or any other approved treatment solution impregnated swan hardwood as described) |  |  |  |  |
| B | 50 X 75mm Rafters | 4.00 | m |  |  |
| C | 50 X 50mm Purlins | 8.00 | m |  |  |
| D | 50 X 100mm wall plate | 4.00 | m |  |  |
| E | 225 x 25mm wrought fascia covered with flat pan | 6.00 | m |  |  |
|  | Doors, Drainage and Plumbing |  |  |  |  |
| A | Supply and fix purpose made 750mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings | 2.00 | No |  |  |
| B | Supply and fix purpose made 800mm x 1900mm metal door made with 2mm thick steel plate framed with 25mm x 50mm steel pipes painted and installed complete with steel frames, padlocks and keys as in indicated in the drawings |  | No |  |  |
| C | Supply and fix purpose made single 900mm x 1600mm see through door made with 25mm x 50mm (2mm gauge) steel pipes and grilled with 25mm square steel pipes as in the drawings on the entrance to the facility painted and installed complete with steel frames, padlocks and keys. | 1.00 | No |  |  |
| D | Provide and Install inspection chambers (2-600mm x 600mm and 1-750mm x 750mm) with precast reinforced concrete cover 75mm thick for each of the compartment | 2.00 | No |  |  |
| E | Provide and Install 1250mm x 900mm chambers with precast reinforced concrete cover 75mm thick for septic tank alternating | 1.00 | No |  |  |
| F | Provide and Install 2400mm long 100mm diameter PVC vent pipe complete with all accessories on all inspection chambers | 2.00 | No |  |  |
| G | Provide approved squat pan completely fixed and connected to drain | 2.00 | No |  |  |
|  | Sub Total Superstructure Works |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | b/f |  |  |  |  |
| H | Provide and install completely approved wash hand basin embedded in block work and 1 water tap in front as indicated in the drawing | 1.00 | No |  |  |
| I | Allow for the provision of purpose made concrete drain finished with vitrified tiles and partitioned at intervals as urinal, running from under the washing to the soak pit as indicated in the drawing | 1.00 | No |  |  |
|  | Physically Challenged Aids |  |  |  |  |
| A | Provide and install approved WC for physically challenged as in the drawing | 1.00 | No |  |  |
| B | Provide and install 25mm GI pipe as hand support rails cast monolithically with the floors slab, braced and supported as indicated the drawing. | 1.00 | No |  |  |
| C | Provide 1:5 sloping ramp on the main entrance to the facility and on the entrance to the physically challenged compartment (4No) | 0.50 | m3 |  |  |
|  | Floor and Wall finishing |  |  |  |  |
| A | 300x300x9mm thick white color floor tiles laid in cement and sand screeded bed (1:4) | 2.20 | m2 |  |  |
| B | 12mm in situ finishing in cement and sand internal and external wall rendering for walls | 37.00 | m2 |  |  |
| C | Fixing of Sanitary tiles (white color) 250mm x400mm on toilet walls (1200mm from the floor) | 8.00 | m2 |  |  |
| D | Supply and fix approved white color vitrified tiles on urinal walls and partitions (up to 150mm top of partition wall) | 3.50 | m2 |  |  |
|  | Painting |  |  |  |  |
| A | Prepare and supply emulsion paint (color to be approved by the Engineer) on all internal walls | 12.00 | m2 |  |  |
| B | Sandblasting (on all external walls leaving out the areas for art work) as specified in the or directed by the Engineer | 14.00 | m2 |  |  |
| C | Metal burglary door and other metal work (3 coats anti-rust finished with approved color as directed by Engineer |  | LS |  |  |
| D | Art work |  | LS |  |  |
|  | Accessories |  |  |  |  |
| A | Provision of bucket for the toilet (minimum of 7 liters) | 2.00 | No |  |  |
| B | Provision of Kettle for the toilet | 2.00 | No |  |  |
|  | Superstructure works carried to summary |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT |
|  | DOUBLE VAULT SEPTIC TANK (Overall dimension 3500mm x 2500mm x1750mm) |  |  |  |  |
| A | Excavation of pit size 3750mmx 2850mm x 1500mm | 17.00 | m3 |  |  |
| B | 100mm Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 1.70 | m3 |  |  |
| C | 100mm apron base Plain in situ concrete mix (1:2:4 mix, 13mm aggr.) on tank base | 0.04 | m3 |  |  |
| D | 225mm thick partition wall (reinforced in situ concrete 1:2:4 mix 19mm aggregate and necessary formwork | 1.20 | m3 |  |  |
| E | 100mm thick cover slab (reinforced in situ concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.90 | m3 |  |  |
| F | 4Nos 600mm x600m x100mm manhole slab (reinforced precast concrete 1:2:4 mix, 19mm aggregate and necessary formwork) | 0.17 | m3 |  |  |
| G | 225mm sand Crete solid block filled with weak concrete in tank walls including partitions built in cement mortar (1:4) | 15.40 | m2 |  |  |
| H | 25mm thick cement and sand (1:4) render on block walls | 15.40 | m2 |  |  |
| I | Plumbing works including all accessories as detailed in the drawing |  | LS |  |  |
| J | Backfill pebbles/broken blocks around and inside the pit | 15.00 | m3 |  |  |
| K | 225mm thick hollow sand Crete block with weep holes (9mm high all round in tank walls built in cement mortar (1:4) | 8.00 | m2 |  |  |
| L | Covering of the weepholes with zinc to prevent short - circuiting | 8.00 | m2 |  |  |
|  | Septic Tank works carried to Summary |  |  |  |  |
|  | SUMMARY OF WORKS |  |  |  |  |
| ITEM | DESCRIPTION |  |  |  | AMOUNT |
| 1.00 | PRELIMINARIES |  |  |  |  |
| 2.00 | SUBSTRUCTURE |  |  |  |  |
| 3.00 | SUPERSTRUCTURE |  |  |  |  |
| 4.00 | SEPTIC TANK |  |  |  |  |
|  | GRAND TOTAL |  |  |  |  |

| Price Offer Sheet (Summary) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item Description | Quantity | Unit of Measure | Unit Price | Total Price |
| 4 compartments pour flush toilet in Shani Motor Park, Gamji Primary School and UBE School Fillin Jirgi. | 3 | Unit |  |  |
| 2 compartments pour flush toilet in Shani Main Market (2 units), Government Secondary School Shani (3 units), Bigaru School Shani (2 units) and GSSS Biu (2 units). | 9 | Unit |  |  |
| As Per Attached BOQ |  |  |  |  |
| Total before tax: |  |  |  |  |
| VAT (if applicable) |  |  |  |  |
| Total: |  |  |  |  |
| Company Name: |  |  |  |  |
| Name of Representative: |  |  |  |  |
| Title: |  |  |  |  |
| Signature: |  |  |  |  |
| Date: |  |  |  |  |
| Tender #: NIG/BIU/TEN11 |  |  |  |  |

# Design Schemes

- No of 2 Toilets

- 4 Nos Toilet Design